## Sprint reviews
| What done | Expected | What done | Expected | What done | Expected | What done | Expected | What done | Expected | What done | Expected | What done | Expected
| 2022-11-09 |  | 2022-11-10 |  | 2022-11-11 |  | 2022-11-14 |  | 2022-11-16 |  | 2022-11-18 |  | ?
Francesco | Analysis | - | Learning about importing in MongoDB | - | check progress and correctness schema + Importing data in DB (w/Marco) | - |  | Latex intro part + importing + 2q+1comm |  | Latex w/ previous queries ready + 1q+2comm
Alessandro | Analysis, document schema | - | Random data generation process | Learning Json py lib | py from txt to json for book text | py from txt to json for book text
Marco | Analysis, document schema | - | Random data generation process | Learning Json py lib | script python modules + Importing data in DB (w/Marco) + generated JSON with ref from py ready to import in DB | progress in random data generation
Lorenzo | document schema | - | - | Check correctness document schema | - | Check correctness document schema |  | Check correctness document schema + 3q + 1 command |  | 2q +1c
Simone | - | - | Latex template | - | - | - |  | 3q + 1 command |  | 2q+1c
[7 empty] | Needed: 50% queries ready |  | Needed: Queries ready |  | Latex ready |  | Revision
[7 empty] | Each query on mongodb doc queries with desc. In english (so they are better described) |  |  |  | Needed: 10q + 5 comm, we do 13q+7 comm
To check complexity of queries